## Sheet1
Gantt Chart
Description
Gantt Chart
This template illustrates a Gantt Chart, also called a Milestone Chart, Project Bar Chart or Activity Chart. A detailed discussion of Gantt Charts can be found at www.ASQ.org
Learn About Gantt Charts
Instructions
● | Enter up to 30 tasks in the cells provided
● | Enter the Start Date for each task and the number of days to complete it.
● | Enter the Pecent Complete for each task.
Learn More
To learn more about other quality tools, visit the ASQ Learn About Quality web site.
Learn About Quality
| Task | Start Date | # Days Required | Percent Complete | Task | Start Date | # Days Required | Percent Complete
| Develop broad plan | 2007-04-03 | 14 | 100
| Present plan to council | 2007-04-20 | 3 | 100
| Identify team | 2007-04-20 | 30 | 100
| Train team | 2007-05-20 | 7 | 100
| Develop detailed plan | 2007-05-27 | 7 | 100
| Conduct preliminary research | 2007-05-25 | 14 | 100
| Identify key practices | 2007-06-07 | 7 | 100
| Identify benchmark partners | 2007-05-25 | 40 | 25
| Collect public data | 2007-06-10 | 21 | 50
| Analyze public data | 2007-07-01 | 21 | 0
| Identify current state | 2007-06-15 | 28 | 0
| Develop benchmark questions | 2007-06-15 | 7 | 0
| Visit benchmark partners | 2007-07-15 | 28 | 0
| Develop new process | 2007-07-28 | 35 | 0
| Present new plan to council | 2007-08-31 | 3 | 0